## Sheet1
Liam's Flavored Chicken Wing Activity Log System
Members:
A. Calimpong, John David
B. Donaire, John Gerard
C. Gitgano, Scott Benzer
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  | September |  | October |  |  |  | November | [8 empty] | December
Tasks | Assignee | Date Started | Date Finished | Status | 30 | 31 | 23 | 24 | 11 | 12 | 13 | 14 | 2 | 3 | 17 | 18 | 21 | 22 | 24 | 29 | 30 | 1 | 3 | 4 | 5 | 8
1. Formulated a draft for the System of Liam's | Calimpong, Donaire, Gitgano | 2024-08-30 | 2024-08-30 | Done | Done | Done | Todo | Done
2. Analysis Description | Calimpong, Donaire, Gitgano | 2024-09-23 | 2024-09-24 | Done
2.1 Function requirements | Donaire | 2024-09-23 | 2024-09-24 | Done
2.2 Logical Model | Gitgano | 2024-09-23 | 2024-09-24 | Done
3. Created a design in FIGMA of Liam's System | Calimpong, Donaire, Gitgano | 2024-10-11 | 2024-10-14 | Done |  |  |  |  | Todo |  |  | Done
3.1 Dashboard and User authentication pages | Calimpong | 2024-10-11 | 2024-10-13 | Done |  |  |  |  | In - Progress |  | Done
3.2 Activity Log and Feedback Pages | Donaire | 2024-10-11 | 2024-10-13 | Done |  |  |  |  | In - Progress |  | Done
3.3 Leave and Branch Management Pages | Gitgano | 2024-10-11 | 2024-10-13 | Done |  |  |  |  | In - Progress |  | Done
4. Implemented the logic of each Pages | Calimpong, Donaire, Gitgano | 2024-11-02 | 2024-12-08 | Done | [8 empty] | Todo | [12 empty] | Done
4.1 At least 4 Recent Logs will now be displayed at the dashboard | Donaire | 22/11/2024 | 24/11/2024 | Done | [13 empty] | In - Progress | Done
4.2 Users can edit their profile | Donaire | 22/112024 | 2024-11-24 | Done | [13 empty] | In - Progress | Done
4.3 User can log activities | Gitgano | 2024-11-22 | 2024-12-04 | Done | [13 empty] | In - Progress | [5 empty] | Done
4.4 User can add feedbacks and comment | Gitgano | 2024-11-22 | 2024-12-03 | Done | [13 empty] | In - Progress |  |  |  |  | Done
4.5 User can apply leave | Calimpong | 2024-12-01 | 2024-12-01 | Done | [17 empty] | Done
4.6 Admin and User restrictions in Activities and Feedback & Comment | Gitgano | 2024-12-05 | 2024-12-05 | Done | [20 empty] | Done
5. Implementation of the UI in all pages | Calimpong, Donaire, Gitgano | 2024-11-02 | 2024-12-08 | Done | [8 empty] | Todo | Done | [11 empty] | Done
5.1 UI design Login and Registration | Donaire | 2024-11-02 | 2024-11-03 | Done | [8 empty] | In - Progress | Done
5.2 UI design of Dashboard | Donaire | 2024-11-17 | 2024-11-21 | Done | [10 empty] | In - Progress |  | Done
5.3 UI design of Leave and Branch | Calimpong | 2024-11-18 | 2024-12-03 | Done | [11 empty] | In - Progress | [6 empty] | Done
5.4 UI design of Branch | Calimpong | 2024-11-18 | 2024-12-03 | Done | [11 empty] | In - Progress | [6 empty] | Done
5.5 UI design of Activity Log | Gitgano | 2024-11-18 | 2024-12-04 | Done | [11 empty] | In - Progress | [7 empty] | Done
5.6 UI design of Feedback and Comments | Gitgano | 18/112024 | 2024-12-04 | Done | [11 empty] | In - Progress | [7 empty] | Done
6. Implementation of default accounts such as Admin and SuperAdmin | Donaire | 2024-11-22 | 2024-11-30 | Done | [13 empty] | Todo |  |  | Done
6.1 Admins can now manage branches and leave request | Donaire | 2024-11-29 | 2024-11-30 | Done | [15 empty] | In - Progress | Done