## Sheet1
Liam's Flavored Chicken Wing Activity Log System
Members:
A. Calimpong, John David
B. Donaire, John Gerard
C. Gitgano, Scott Benzer
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Formulated a draft for the System of Liam's | ABC | 2024-08-30 | 2024-08-31 | Done
2. Analysis Description | A | 2024-09-23 | 2024-09-23 | Done
2.1 Function requirements | B | 2024-09-23 | 2024-09-23 | Done
2.2 Logical Model | C | 2024-09-23 | 2024-09-23 | Done
3. Created a design in FIGMA of Liam's System | ABC | 2024-10-11 | 2024-10-14 | Done
3.1 Dashboard and User authentication pages | A | 2024-10-11 | 2024-10-13 | Done
3.2 Activity Log and Feedback Pages | B | 2024-10-11 | 2024-10-13 | Done
3.3 Leave and Branch Management Pages | C | 2024-10-11 | 2024-10-13 | Done
4. Implemented its pages to Django | ABC | 2024-11-02 | 2024-11-03 | In - Progress
4.1 User Authentication Pages | A | 2024-11-02 | 2024-11-03 | Done
5. UI design of Leave and Branch | A | 2024-11-18 | 2024-11-19 | Done