## Sheet1
Liam's Flavored Chicken Wing Activity Log System
Members:
A. Calimpong, John David
B. Donaire, John Gerard
C. Gitgano, Scott Benzer
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  | September | October |  |  |  | November
Tasks | Assignee | Date Started | Date Finished | Status | 30 | 31 | 23 | 11 | 12 | 13 | 14 | 2 | 3 | 17 | 18 | 21 | 22 | 29 | 30
1. Formulated a draft for the System of Liam's | ABC | 2024-08-30 | 2024-08-31 | Done | Done | Done | Done
2. Analysis Description | Calimpong | 2024-09-23 | 2024-09-23 | Done
2.1 Function requirements | Donaire | 2024-09-23 | 2024-09-23 | Done
2.2 Logical Model | Gitgano | 2024-09-23 | 2024-09-23 | Done
3. Created a design in FIGMA of Liam's System | ABC | 2024-10-11 | 2024-10-14 | Done |  |  |  | In - Progress |  |  | Done
3.1 Dashboard and User authentication pages | Calimpong | 2024-10-11 | 2024-10-13 | Done |  |  |  | In - Progress |  | Done
3.2 Activity Log and Feedback Pages | Donaire | 2024-10-11 | 2024-10-13 | Done |  |  |  | In - Progress |  | Done
3.3 Leave and Branch Management Pages | Gitgano | 2024-10-11 | 2024-10-13 | Done |  |  |  | In - Progress |  | Done
4. Implemented its pages to Django | ABC | 2024-11-02 |  | In - Progress | [7 empty] | In - Progress | Done
4.1 UI design Login and Registration | Donaire | 2024-11-02 | 2024-11-03 | Done | [7 empty] | In - Progress | Done
4.2 UI design of Dashboard | Donaire | 2024-11-17 | 2024-11-21 | Done | [9 empty] | In - Progress |  | Done
4.3 UI design of Leave and Branch | Calimpong | 2024-11-18 |  | In - Progress | [10 empty] | In - Progress
4.4 UI design of Activity Log and Feedback and Comments | Gitgano | 2024-11-18 |  | In - Progress | [10 empty] | In - Progress
5. Implementation of default accounts such as Admins | Donaire | 2024-11-22 | 2024-11-30 | Done | [12 empty] | In - Progress |  | Done
5.1 Admins can now manage branches and leave request | Donaire | 2024-11-29 | 2024-11-30 | Done | [13 empty] | In - Progress | Done